## DRAFT OF

TheNeighborhood Services Community Development

CAPER FY2024-2025

Consolidated Annual

Performance and

Evaluation Report

(Please note that this report is Not Totally Complete. Information is still being gathered and in process)

## CR-05 - Goals and Outcomes

Progress the jurisdiction has made in carrying out its strategic plan and its action plan.  91.520(a)

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

To comply with regulations set forth by the United States Department of Housing and Urban Development (HUD) regarding the Consolidated Annual Performance Evaluation Report (CAPER), this document provides the public and HUD with an assessment of the City of Tyler, Texas' accomplishments in utilizing these funds from October 1, 2024, to September 30, 2025. The CDBG and HOME grant funds must be expended with services and/or activities to meet one or more of the three (3) National Objectives set by HUD: 1. To benefit low-to-moderate income persons and families, 2. To prevent, reduce, or eliminate slum and blight, or 3. Meet an urgent community need (ex., disaster relief).
 First-Time Homebuyers, like many cities, Tyler has been significantly affected by inflation in recent years. The housing market has experienced considerable shifts in material costs, housing prices, annual percentage rates for home loans, and the required down payments for most conventional and FHA loans. Due to a restricted supply chain and building materials costs, the average cost of housing has risen from approximately $100 per square foot to between $175 and $220. This increase created major challenges for low- to moderate-income families hoping to transition into homeownership. For example, a modest 1,300-square-foot home that once cost $130,000 now exceeds $227,500 in many areas. Furthermore, homes that remained relatively affordable were often not up to code or move-in ready. As a result, staff decided to place the First-Time Homebuyers Program on hiatus in 2022 to review and improve it. After collaborating with community leaders, lenders, other cities, and consultants to develop a program that would better meet the community's evolving needs. The application process has been simplified, and assistance levels adjusted. However, in PY 25, five houses in the Hidden Palace Subdivision were completed and sold to Low/Mod Income buyers, completing the second phase of the Hidden Palace Subdivision. Additionally, three new construction projects have started. They are planned for completion, with all three under contract with low/moderate income homebuyers in PY 25 as Phase 2 of the Hidden Palace Subdivision. 
 Public Facilities - the Nobel E Young Park renovations have been completed, featuring a complete park makeover.
 Public Services - The City of Tyler works with local agencies to identify temporary housing needs for our homeless population during severe weather events. Partnerships and program development are still under review.

Reducing Substandard Structures - The City of Tyler identified 48 homes that were dilapidated and/or in severe code violations. The city is working with those homeowners to rehab the houses, and/or the Neighborhood Revitalization Board is updating their policies to help streamline demoing the identified substandard structures. The City demolished and removed debris on ten substandard structures.

Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives.  91.520(g)

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

| Goal | Category | Source / Amount | Indicator | Unit of Measure | Expected – Strategic Plan | Actual – Strategic Plan | Percent Complete | Expected – Program Year | Actual – Program Year | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CDBG/HOME Admin. | Affordable Housing Public Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG: $ / HOME: $ | Other | Other | 3 | 0 | 0.00% |  |  |  |
| CHDO Reserve | Affordable Housing Homeless | HOME: $ | Homeowner Housing Added | Household Housing Unit | 20 | 0 | 0.00% |  |  |  |
| Homebuyers | Affordable Housing | CDBG: $60000 / HOME: $ | Homeowner Housing Added | Household Housing Unit | 0 | 4 |  | 0 | 4 |  |
| Homebuyers | Affordable Housing | CDBG: $60000 / HOME: $ | Direct Financial Assistance to Homebuyers | Households Assisted | 25 | 0 | 0.00% | 5 | 0 | 0.00% |
| New Construction/Reconstruction | Affordable Housing | HOME: $ | Homeowner Housing Added | Household Housing Unit | 15 | 0 | 0.00% | 6 | 0 | 0.00% |
| New Construction/Reconstruction | Affordable Housing | HOME: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 0 | 1 |  | 0 | 1 |  |
| Public Facilities | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 2000 | 0 | 0.00% | 500 | 0 | 0.00% |
| Single Family Housing Goals | Affordable Housing Homeless | CDBG: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 100 | 18 | 18.00% | 15 | 18 | 120.00% |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.

## CR-10 - Racial and Ethnic composition of families assisted

Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)

|  | CDBG | HOME |
| --- | --- | --- |
| White | 0 | 1 |
| Black or African American | 0 | 25 |
| Asian | 0 | 0 |
| American Indian or American Native | 0 | 0 |
| Native Hawaiian or Other Pacific Islander | 0 | 0 |

| Total | 0 | 26 |
| --- | --- | --- |

| Hispanic | 0 | 1 |
| --- | --- | --- |
| Not Hispanic | 0 | 25 |

Table 2 – Table of assistance to racial and ethnic populations by source of funds

Narrative

## CR-15 - Resources and Investments 91.520(a)

Identify the resources made available

| Source of Funds | Source | Resources Made Available | Amount Expended During Program Year |
| --- | --- | --- | --- |
| CDBG | public - federal | 755,127 |  |
| HOME | public - federal | 304,153 |  |

Table 3 - Resources Made Available

Narrative

Identify the geographic distribution and location of investments

| Target Area | Planned Percentage of Allocation | Actual Percentage of Allocation | Narrative Description |
| --- | --- | --- | --- |
| City of Tyler | 100 |  |  |

Table 4 – Identify the geographic distribution and location of investments

Narrative

Leveraging

Explain how federal funds  leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.

| Fiscal Year Summary – HOME Match |  |
| --- | --- |
| 1. Excess match from prior Federal fiscal year |  |
| 2. Match contributed during current Federal fiscal year |  |
| 3 .Total match available for current Federal fiscal year (Line 1 plus Line 2) |  |
| 4. Match liability for current Federal fiscal year |  |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) |  |

Table 5 – Fiscal Year Summary - HOME Match Report

| Match Contribution for the Federal Fiscal Year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project No. or Other ID | Date of Contribution | Cash (non-Federal sources) | Foregone Taxes, Fees, Charges | Appraised Land/Real Property | Required Infrastructure | Site Preparation, Construction Materials, Donated labor | Bond Financing | Total Match |

Table 6 – Match Contribution for the Federal Fiscal Year

HOME MBE/WBE report

| Program Income – Enter the program amounts for the reporting period |  |  |  |  |
| --- | --- | --- | --- | --- |
| Balance on hand at begin-ning of reporting period $ | Amount received during reporting period $ | Total amount expended during reporting period $ | Amount expended for TBRA $ | Balance on hand at end of reporting period $ |

Table 7 – Program Income

Minority Business Enterprises and Women Business Enterprises – Indicate the number and dollar value of contracts for HOME projects completed during the reporting period

|  | Total | Minority Business Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |

| Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number |  |  |  |  |  |  |
| Dollar Amount |  |  |  |  |  |  |

| Sub-Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number |  |  |  |  |  |  |
| Dollar Amount |  |  |  |  |  |  |

|  | Total | Women Business Enterprises | Male |
| --- | --- | --- | --- |

| Contracts |  |  |  |
| --- | --- | --- | --- |
| Number |  |  |  |
| Dollar Amount |  |  |  |

| Sub-Contracts |  |  |  |
| --- | --- | --- | --- |
| Number |  |  |  |
| Dollar Amount |  |  |  |

Table 8 - Minority Business and Women Business Enterprises

Minority Owners of Rental Property – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted

|  | Total | Minority Property Owners |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number |  |  |  |  |  |  |
| Dollar Amount |  |  |  |  |  |  |

Table 9 – Minority Owners of Rental Property

Relocation and Real Property Acquisition – Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition

|  | Number | Cost |
| --- | --- | --- |
| Parcels Acquired |  |  |
| Businesses Displaced |  |  |
| Nonprofit Organizations Displaced |  |  |
| Households Temporarily Relocated, not Displaced |  |  |

| Households Displaced | Total | Minority Property Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number |  |  |  |  |  |  |
| Cost |  |  |  |  |  |  |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 0 | 0 |
| Number of Non-Homeless households to be provided affordable housing units | 29 | 0 |
| Number of Special-Needs households to be provided affordable housing units | 0 | 0 |
| Total | 29 | 0 |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 0 | 0 |
| Number of households supported through The Production of New Units | 4 | 0 |
| Number of households supported through Rehab of Existing Units | 20 | 0 |
| Number of households supported through Acquisition of Existing Units | 0 | 0 |
| Total | 24 | 0 |

Table 12 – Number of Households Supported

Discuss the difference between goals and outcomes and problems encountered in meeting these goals.

Discuss how these outcomes will impact future annual action plans.

Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.

| Number of Households Served | CDBG Actual | HOME Actual |  |
| --- | --- | --- | --- |
| Extremely Low-income | 2 | 0 |
| Low-income | 2 | 1 |
| Moderate-income | 0 | 1 |
| Total | 4 | 2 |

Table 13 – Number of Households Served

Narrative Information

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:

Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs

Addressing the emergency shelter and transitional housing needs of homeless persons

Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are:  likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions);  and,  receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs

Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again

## CR-30 - Public Housing 91.220(h); 91.320(j)

Actions taken to address the needs of public housing

Actions taken to encourage public housing residents to become more involved in management and participate in homeownership

Actions taken to provide assistance to troubled PHAs

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)

Actions taken to address obstacles to meeting underserved needs.  91.220(k); 91.320(j)

Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)

Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)

Actions taken to develop institutional structure. 91.220(k); 91.320(j)

Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)

Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice.  91.520(a)

## CR-40 - Monitoring 91.220 and 91.230

Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements

Citizen Participation Plan 91.105(d); 91.115(d)

Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports.

## CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?

[BEDI grantees]  Describe accomplishments and program outcomes during the last year.

## CR-50 - HOME 24 CFR 91.520(d)

Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations

Please list those projects that should have been inspected on-site this program year based upon the schedule in 24 CFR §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 24 CFR 91.520(e) and 24 CFR 92.351(a)

Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics

Describe other actions taken to foster and maintain affordable housing. 24 CFR 91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing). 24 CFR 91.320(j)

## CR-58 – Section 3

Identify the number of individuals assisted and the types of assistance provided

| Total Labor Hours | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Total Number of Activities | 0 | 0 | 0 | 0 | 0 |
| Total Labor Hours |  |  |  |  |  |
| Total Section 3 Worker Hours |  |  |  |  |  |
| Total Targeted Section 3 Worker Hours |  |  |  |  |  |

Table 14 – Total Labor Hours

| Qualitative Efforts - Number of Activities by Program | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Outreach efforts to generate job applicants who are Public Housing Targeted Workers |  |  |  |  |  |
| Outreach efforts to generate job applicants who are Other Funding Targeted Workers. |  |  |  |  |  |
| Direct, on-the job training (including apprenticeships). |  |  |  |  |  |
| Indirect training such as arranging for, contracting for, or paying tuition for, off-site training. |  |  |  |  |  |
| Technical assistance to help Section 3 workers compete for jobs (e.g., resume assistance, coaching). |  |  |  |  |  |
| Outreach efforts to identify and secure bids from Section 3 business concerns. |  |  |  |  |  |
| Technical assistance to help Section 3 business concerns understand and bid on contracts. |  |  |  |  |  |
| Division of contracts into smaller jobs to facilitate participation by Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with assistance in seeking employment including: drafting resumes,preparing for interviews, finding job opportunities, connecting residents to job placement services. |  |  |  |  |  |
| Held one or more job fairs. |  |  |  |  |  |
| Provided or connected residents with supportive services that can provide direct services or referrals. |  |  |  |  |  |
| Provided or connected residents with supportive services that provide one or more of the following: work readiness health screenings, interview clothing, uniforms, test fees, transportation. |  |  |  |  |  |
| Assisted residents with finding child care. |  |  |  |  |  |
| Assisted residents to apply for, or attend community college or a four year educational institution. |  |  |  |  |  |
| Assisted residents to apply for, or attend vocational/technical training. |  |  |  |  |  |
| Assisted residents to obtain financial literacy training and/or coaching. |  |  |  |  |  |
| Bonding assistance, guaranties, or other efforts to support viable bids from Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with training on computer use or online technologies. |  |  |  |  |  |
| Promoting the use of a business registry designed to create opportunities for disadvantaged and small businesses. |  |  |  |  |  |
| Outreach, engagement, or referrals with the state one-stop system, as designed in Section 121(e)(2) of the Workforce Innovation and Opportunity Act. |  |  |  |  |  |
| Other. |  |  |  |  |  |

Table 15 – Qualitative Efforts - Number of Activities by Program

Narrative